## Growth Deal
Dorset LEP Growth Deal Forward Plan
Project Delivery
Due Diligence
Grant Agreement
Date: July 2022 |  |  | Preliminary Funding Agreement
Project Complete
|  | 2015/2016 | [11 empty] | 2016/2017 | [11 empty] | 2017/2018 | [11 empty] | 2018/2019 | [11 empty] | 2019/2020 | [11 empty] | 2020/2021
Project Title | Organisation | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
BIG Programme | Dorset Council/BCP Council
A338 Reconstruction | Dorset Council | bar: 2015/2016 Jan to 2018/2019 Apr
A338 Blackwater Junction & A338 Widening | Dorset Council | 2017/2018 Aug: Phase 1 - East Junction; 2018/2019 Sep: Phase 2 Auxillary Lanes; 2019/2020 Jul: Phase 3 - West Junction
Cooper Dean | Dorset Council | bar: 2018/2019 Nov to 2019/2020 Jun
Wessex Fields | BCP Council | bar: 2016/2017 Apr to 2020/2021 Feb
A348/ FWP Corridor | BCP Council | bar: 2018/2019 Aug to 2020/2021 Mar
B3073 Chapel Gate | Dorset Council | bar: 2015/2016 Jan to 2018/2019 May
B3073 Hurn Roundabout | Dorset Council | bar: 2017/2018 Apr to 2018/2019 Oct
Parley West | Dorset Council | bar: 2017/2018 Apr to 2018/2019 Oct
South East Dorset Urban Mobility Strategy | AECOM | bar: 2018/2019 Jan to 2020/2021 Sep
Port of Poole Infrastructure Programme | BCP Council
Cabot Lane/Broadstone Way | BCP Council | bar: 2019/2020 Apr to 2020/2021 Jan
Darby's Corner | BCP Council | bar: 2019/2020 Apr to 2020/2021 Jun
Gravel Hill Online Improvements | BCP Council | bar: 2016/2017 Apr to 2017/2018 May
Dunyeats | BCP Council | bar: 2016/2017 Apr to 2017/2018 May
Hatch Pond | BCP Council | bar: 2016/2017 Apr to 2017/2018 May
Poole Bridge Approach Spans | BCP Council | bar: 2015/2016 Apr to 2017/2018 Dec
Townside Access to Port of Poole | BCP Council | bar: 2016/2017 Jun to 2020/2021 Mar
Gillingham Access to Growth | Dorset Council | bar: 2017/2018 Apr to 2020/2021 Mar
Wallisdown Road/ Boundary Roundabout | BCP Council | bar: 2018/2019 Apr to 2020/2021 Mar
Agri-tech Centre | Kingston Maurward College | bar: 2015/2016 Nov to 2016/2017 Jul
Construction and Engineering Project | Bournemouth & Poole College | bar: 2019/2020 Aug to 2020/2021 Feb
Outdoor Education Centre & Estates | Kingston Maurward College | bar: 2019/2020 Aug to 2019/2020 Mar
IT Infrastructure Upgrade | Kingston Maurward College | bar: 2019/2020 Dec to 2020/2021 Feb
New Green Classroom | Kingston Maurward College | bar: 2019/2020 Dec to 2020/2021 Mar
Motor Vehicle Centre of Excellence | Weymouth College | bar: 2019/2020 Jun to 2019/2020 Nov
Engineering Centre of Excellence | Weymouth College | bar: 2019/2020 Jun to 2020/2021 Mar
Engineering & Manufacturing Project | Bournemouth and Poole College | bar: 2015/2016 Nov to 2016/2017 Oct
Finance & Business Project | Bournemouth and Poole College | bar: 2015/2016 Nov to 2016/2017 Oct
Digital Design | Bournemouth and Poole College | bar: 2019/2020 Dec to 2020/2021 Jun
Digital and Enterprise Innovation Hub | Bournemouth and Poole College | bar: 2019/2020 Dec to 2020/2021 Jan
AUB Innovation Studio | Arts University Bournemouth | bar: 2017/2018 Apr to 2020/2021 Mar
LapSafe Learning | Arts University Bournemouth | bar: 2019/2020 Aug to 2019/2020 Mar
Orthopaedic Research Institute (ORI) | Bournemouth University | 2015/2016 Oct: Phase 1 Complete; 2017/2018 Jan: Phase 2
Institute For Medical Imaging & Visualisation | Bournemouth University | bar: 2017/2018 Jan to 2019/2020 Mar
Eden Portland | MEMO | bar: 2017/2018 Apr to 2018/2019 Mar
Jurassica | MEMO | bar: 2015/2016 Apr
Mary Anning Wing | Lyme Regis Museum | bar: 2017/2018 Jul to 2017/2018 Mar
Shire Hall | Shire Hall | bar: 2017/2018 Jun to 2018/2019 Apr
Swanage Pier | Swanage Pier Trust | bar: 2017/2018 Aug to 2018/2019 Mar
Smart Place Pilot | BCP Council | bar: 2019/2020 Jun to 2020/2021 Mar
Smart Place Investment Plan | BCP Council | bar: 2020/2021 Apr to 2020/2021 Mar
Lansdowne Business District | BCP Council | bar: 2017/2018 Apr to 2020/2021 Mar
Defence BattleLab | Dorset Council | bar: 2019/2020 Jul to 2020/2021 Mar
Literary & Scientific Institute (LSI) | LSI Bridport | bar: 2017/2018 Apr to 2018/2019 Mar
Quadrant - Dorset Innovation Park | Dorset Innovation Park | bar: 2016/2017 Oct to 2017/2018 Mar
Holes Bay | BCP Council | bar: 2017/2018 Aug to 2020/2021 Sep
Western Growth Corridor | Dorset Council | bar: 2015/2016 Nov to 2016/2017 Mar
Stewarts Agri-tech Glasshouse | D.Stewart & Son, Limited | bar: 2019/2020 Apr to 2019/2020 Mar
Histopathology Diagnostic Hub for Dorset | Royal Bournemouth Hospital | bar: 2019/2020 Mar to 2020/2021 Mar
Centre of Excellence for Construction Skills | Weymouth College | bar: 2019/2020 Mar to 2020/2021 Mar
AUB Innovation Suite | Arts University Bournemouth | bar: 2020/2021 Aug to 2020/2021 Mar
AUB Innovation Resources | Arts University Bournemouth | bar: 2020/2021 Aug to 2020/2021 Mar
Workstations | Bournemouth & Poole College | bar: 2020/2021 Aug to 2020/2021 Mar
Remote Access to Resources | Bournemouth & Poole College | bar: 2020/2021 Aug to 2020/2021 Mar

## Getting Building Fund
Dorset LEP Getting Building Fund Forward Plan
Project Delivery
Due Diligence
Grant Agreement
Date: July 2022 |  |  | Project Complete
|  | 2020/2021 | [11 empty] | 2021/2022
Project Title | Organisation | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
University Centre & Rural Business Development Hub | Kingston Maurward College
Network Infrastructure | Bournemouth & Poole College
Higher Education Centre | Weymouth College
Integrated Rehabilitation Centre | AECC University College
Dorset Clinical Trials Unit | University Hospitals Dorset NHS Trust
Border Control Post | Poole Harbour Commissioners
Public Trade Office | Poole Harbour Commissioners
Remote Management of Hypertension | Dorset NHS Clinical Commissioning Group
Fibre Hub Connectivity in Rural Dorset | Dorset Council

## Growing Places Fund
Dorset LEP Growing Places Fund
Forward Plan
|  | Due Dilligence | [5 empty] | Loan repayment deadline
|  | Project Complete | [5 empty] | Loan agreement signed
|  | Project implemenation | [5 empty] | Project delivery delay
Date: July 2022
| 2012/2013 |  |  |  |  | 2013/2014 |  |  |  |  | 2014/2015 |  |  |  | 2015/2016 |  |  |  | 2016/2017 |  |  |  | 2017/2018 |  |  |  | 2018/2019 |  |  |  | 2019/2020 |  |  |  | 2020/2021 |  |  |  | 2021/2022 |  |  |  | 2022/2023 |  |  |  | 2023/2024 |  |  |  | 2024/2025 |  |  |  | 2025/2026
Project Title | Q1 |  | Q2 | Q3 | Q4 | Q1 | Q2 |  | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Alder Hills
Bionanovate
Boscome Regeneration
Castle Court
Cobham Gate
Field International
Hamworthy
North Dorset Business Park
Ultrafast Broadband
Kingston Maurward College
Stokeford Renewable Grid Connection
Dorset Green H2
Agri-tech Innovation Centre