## Growth Deal
Dorset LEP Growth Deal Forward Plan
Project Delivery
Due Diligence
Grant Agreement
Date: Aug 2020 |  |  | Preliminary Funding Agreement
Project Complete
|  | 2015/2016 | [11 empty] | 2016/2017 | [11 empty] | 2017/2018 | [11 empty] | 2018/2019 | [11 empty] | 2019/2020 | [11 empty] | 2020/2021 | [11 empty] | Status
Project Title | Organisation | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
BIG Programme | Dorset Council/BCP Council | [72 empty] | O
A338 Reconstruction | Dorset Council | [72 empty] | C | bar: 2015/2016 Jan to 2018/2019 Apr
A338 Blackwater Junction & A338 Widening | Dorset Council | 2017/2018 Aug: Phase 1 - East Junction; 2018/2019 Sep: Phase 2 Auxillary Lanes; 2019/2020 Jul: Phase 3 - West Junction | O
Cooper Dean | Dorset Council | [72 empty] | C | bar: 2018/2019 Nov to 2019/2020 Jun
Wessex Fields | BCP Council | [72 empty] | O | bar: 2016/2017 Apr to 2020/2021 Dec
A348/ FWP Corridor | BCP Council | [72 empty] | O | bar: 2018/2019 Aug to 2020/2021 Mar
B3073 Chapel Gate | Dorset Council | [72 empty] | C | bar: 2015/2016 Jan to 2018/2019 May
B3073 Hurn Roundabout | Dorset Council | [72 empty] | C | bar: 2017/2018 Apr to 2018/2019 Oct
Parley West | Dorset Council | [72 empty] | C | bar: 2017/2018 Apr to 2018/2019 Oct
South East Dorset Urban Mobility Strategy | AECOM | [72 empty] | O | bar: 2018/2019 Jan to 2020/2021 Sep
Port of Poole Infrastructure Programme | BCP Council | [72 empty] | O
Cabot Lane/Broadstone Way | BCP Council | [72 empty] | O | bar: 2019/2020 Apr to 2020/2021 Jan
Darby's Corner | BCP Council | [72 empty] | C | bar: 2019/2020 Apr to 2020/2021 Jun
Gravel Hill Online Improvements | BCP Council | [72 empty] | C | bar: 2016/2017 Apr to 2017/2018 May
Dunyeats | BCP Council | [72 empty] | C | bar: 2016/2017 Apr to 2017/2018 May
Hatch Pond | BCP Council | [72 empty] | C | bar: 2016/2017 Apr to 2017/2018 May
Poole Bridge Approach Spans | BCP Council | [72 empty] | C | bar: 2015/2016 Apr to 2017/2018 Dec
Townside Access to Port of Poole | BCP Council | [72 empty] | O | bar: 2016/2017 Jun to 2020/2021 Mar
Gillingham Access to Growth | Dorset Council | [72 empty] | O | bar: 2017/2018 Apr to 2020/2021 Mar
Wallisdown Road/ Boundary Roundabout | BCP Council | [72 empty] | O | bar: 2018/2019 Apr to 2020/2021 Mar
Agri-tech Centre | Kingston Maurward College | [72 empty] | C | bar: 2015/2016 Nov to 2016/2017 Jul
Construction and Engineering Project | Kingston Maurward College | [72 empty] | O | bar: 2019/2020 Aug to 2020/2021 Sep
Outdoor Education Centre & Estates | Kingston Maurward College | [72 empty] | O | bar: 2019/2020 Aug to 2019/2020 Mar
IT Infrastructure Upgrade | Kingston Maurward College | [72 empty] | O | bar: 2019/2020 Dec to 2020/2021 Dec
New Green Classroom | Kingston Maurward College | [72 empty] | O | bar: 2019/2020 Dec to 2020/2021 Sep
Motor Vehicle Centre of Excellence | Weymouth College | [72 empty] | C | bar: 2019/2020 Jul to 2019/2020 Nov
Engineering Centre of Excellence | Weymouth College | [72 empty] | O | bar: 2019/2020 Aug to 2020/2021 Sep
Engineering & Manufacturing Project | Bournemouth and Poole College | [72 empty] | C | bar: 2015/2016 Nov to 2016/2017 Oct
Finance & Business Project | Bournemouth and Poole College | [72 empty] | C | bar: 2015/2016 Nov to 2016/2017 Oct
Digital Design | Bournemouth and Poole College | [72 empty] | O | bar: 2019/2020 Dec to 2020/2021 Jun
Digital and Enterprise Innovation Hub | Bournemouth and Poole College | [72 empty] | O | bar: 2019/2020 Dec to 2020/2021 Oct
AUB Innovation Studio | Arts University Bournemouth | [72 empty] | O | bar: 2017/2018 Apr to 2020/2021 Sep
LapSafe Learning | Arts University Bournemouth | [72 empty] | O | bar: 2019/2020 Aug to 2019/2020 Mar
Orthopaedic Research Institute (ORI) | Bournemouth University | 2015/2016 Oct: Phase 1 Complete; 2017/2018 Jan: Phase 2 | O
Institute For Medical Imaging & Visualisation | Bournemouth University | [72 empty] | C | bar: 2017/2018 Jan to 2019/2020 Mar
Eden Portland | MEMO | [72 empty] | C | bar: 2017/2018 Apr to 2018/2019 Mar
Jurassica | MEMO | [72 empty] | C | bar: 2015/2016 Apr
Mary Anning Wing | Lyme Regis Museum | [72 empty] | C | bar: 2017/2018 Jul to 2017/2018 Mar
Shire Hall | Shire Hall | [72 empty] | C | bar: 2017/2018 Jun to 2018/2019 Apr
Swanage Pier | Swanage Pier Trust | [72 empty] | C | bar: 2017/2018 Aug to 2018/2019 Mar
5G/Dorset Digital Pilot | BCP Council | [72 empty] | O | bar: 2019/2020 Jun to 2020/2021 Mar
Smart Place Investment Plan | BCP Council | [72 empty] | O | bar: 2020/2021 Apr to 2020/2021 Mar
Lansdowne Business District | BCP Council | [72 empty] | O | bar: 2017/2018 Apr to 2020/2021 Mar
Defence Innovation Centre | Dorset Council | [72 empty] | O | bar: 2019/2020 Jul to 2020/2021 Mar
Literary & Scientific Institute (LSI) | LSI Bridport | [72 empty] | C | bar: 2017/2018 Apr to 2018/2019 Mar
Quadrant - Dorset Innovation Park | Dorset Innovation Park | [72 empty] | C | bar: 2016/2017 Oct to 2017/2018 Mar
Holes Bay | BCP Council | [72 empty] | O | bar: 2017/2018 Aug to 2020/2021 Mar
Western Growth Corridor | Dorset Council | [72 empty] | C | bar: 2015/2016 Nov to 2016/2017 Mar
Stewarts Agri-tech Glasshouse | D.Stewart & Son, Limited | [72 empty] | C | bar: 2019/2020 Apr to 2019/2020 Mar
Histopathology Diagnostic Hub for Dorset | Royal Bournemouth Hospital | [72 empty] | O | bar: 2019/2020 Mar to 2020/2021 Mar
Centre of Excellence for Construction Skills | Weymouth College | [72 empty] | O | bar: 2019/2020 Mar to 2020/2021 Mar

## Dorset Gateway
Dorset Gateway Forward Plan
Business as usual
|  | Targeted activity |  |  |  |  | Reporting deadline | [5 empty] | Preliminary Funding Agreement
|  | Planning activity |  |  |  |  | Meeting | [5 empty] | Grant Agreement
Date: Aug 2020 |  | Contract delivery |  |  |  |  | Project Complete | [5 empty] | End Date Slippage
| 2018/2019 | [11 empty] | 2019/2020 | [11 empty] | 2020/2021
Project Title | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
DORSET GATEWAY | bar: 2018/2019 Apr
Management, governance and coordination
Performance and Investment Committee | bar: 2019/2020 Nov; 2019/2020 Jan; 2019/2020 Mar; 2020/2021 May
bi-monthly Board reporting | bar: 2018/2019 Nov; 2018/2019 Jan; 2018/2019 Mar; 2019/2020 May; 2019/2020 Jul; 2019/2020 Sep; 2019/2020 Nov; 2019/2020 Jan; 2019/2020 Mar; 2020/2021 May; 2020/2021 Jul; 2020/2021 Sep; 2020/2021 Nov; 2020/2021 Jan; 2020/2021 Mar
Project evaluation | bar: 2019/2020 Feb to 2020/2021 Apr
Data, monitoring, reporting, valuation and value for money
Bi-annual reporting to BEIS | bar: 2018/2019 Oct; 2019/2020 Apr; 2019/2020 Oct; 2020/2021 Apr; 2020/2021 Oct; 2020/2021 Mar
Business Support scorecard | bar: 2018/2019 Jan to 2020/2021 Mar
CRM development and reporting | bar: 2018/2019 Jan to 2020/2021 Mar
Strategic partnerships and business support simplification
Developing marketing materials | bar: 2018/2019 Aug to 2018/2019 Jan; 2019/2020 Oct to 2019/2020 Mar
Marketing the service to the business community | bar: 2018/2019 Oct to 2020/2021 Mar
Website reviewed and updated | bar: 2018/2019 Oct to 2018/2019 Mar
Communications to delivery partners | bar: 2018/2019 Oct to 2020/2021 Mar
Triage, diagnostic and signposting
Custom Brokerage Service delivery
Mapping of business support provision | bar: 2018/2019 Sep to 2018/2019 Oct; 2020/2021 Apr
Delivery principles agreed with delivery partners | bar: 2019/2020 Feb to 2020/2021 Apr
Ambitious and high growth businesses (Scale-Ups
Bid Writing Support Service
Scale-up support workpackage | bar: 2019/2020 Sep to 2020/2021 Apr; 2020/2021 Jul to 2020/2021 Mar
Bid writing workshops | bar: 2018/2019 Oct to 2018/2019 Feb; 2019/2020 Sep to 2019/2020 Dec; 2019/2020 Mar; 2020/2021 May; 2020/2021 Jul; 2020/2021 Oct; 2020/2021 Mar
Business Resilience: COVID-19 and Brexit
Business support packages | bar: 2019/2020 Dec to 2020/2021 Sep
Workshops/Webinars | bar: 2019/2020 Sep to 2020/2021 Jul
Research activity | bar: 2019/2020 Jan to 2020/2021 Sep
Partnership meetings | bar: 2019/2020 Dec to 2020/2021 Oct
Government reporting | bar: 2019/2020 Oct to 2020/2021 Mar

## Growing Places Fund
Dorset LEP Growing Places Fund
Delivery Plan
|  | Due Dilligence | [5 empty] | Loan repayment deadline
|  | Project Complete | [5 empty] | Loan agreement signed
|  | Project implemenation | [5 empty] | Project delivery delay
Date: Aug 2020
| 2012/2013 |  |  |  |  | 2013/2014 |  |  |  |  | 2014/2015 |  |  |  | 2015/2016 |  |  |  | 2016/2017 |  |  |  | 2017/2018 |  |  |  | 2018/2019 |  |  |  | 2019/2020 |  |  |  | 2020/2021 |  |  |  | 2021/2022
Project Title | Q1 |  | Q2 | Q3 | Q4 | Q1 | Q2 |  | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Alder Hills
Bionanovate
Boscome Regeneration
Castle Court
Cobham Gate
Field International
Hamworthy
North Dorset Business Park
Ultrafast Broadband
Kingston Maurward College | [42 empty] | Loan repayment due date: Dec 2023