## Growth Deal
DORSET LOCAL ENTERPRISE PARTNERSHIP
Growth Deal Project Dashboard
REPORT DATE
2020-05-01
PROJECT INFORMATION | [9 empty] | FINANCIAL INFORMATION |  |  |  | OUPUTS AND OUTCOMES
PROJECT NAME | PROJECT DELIVERY PARTNER | PROJECT LOCATION | PROJECT THEME | PROJECT START DATE | PROJECT END DATE | % TIME COMPLETE | PROJECT STATUS | PROJECT SUMMARY |  | TOTAL PROJECT BUDGET | TOTAL GROWTH DEAL FUNDING | SPENT TO DATE | % SPENT TO DATE | FORECAST OUTPUTS | PROGRESS TOWARDS FORECAST | FORECAST OUTCOMES BY 2025 | PROGRESS TOWARDS FORECAST
Bournemouth International Growth (BIG) Programme | Bournemouth Borough Council & Dorset County Council | Bournemouth | Transport | 2015-04-01 | 2021-03-31 | 84.76% | Ongoing | Major economic growth plan focused on improving connectivity, easing congestion, protecting existing jobs and creating new ones in and around Bournemouth Airport and Wessex Fields. |  | 49692346.36 | 41024246 | 37197035 | 90.67% | Reconstruction of A338, improvements to Blackwater Junction, Chapel Gate and Hurn Roundabout, widening between Blackwater-Cooper Dean, proposed new junction at Wessex Fields, improvements along A348 corridor. | On Target | - Create 10,000 jobs - Release 60HA of employment land - Generate up to £500m GVA - Deliver 350 homes | On Target
Port of Poole Infrastructure Programme | Bournemouth, Christchurch and Poole Council (BCP) | Poole | Transport | 2015-04-01 | 2021-03-31 | 84.76% | Ongoing | Six transport schemes to improve access into and around the Port of Poole. The investment will help drive local economic growth and bring an anticipated £500 million of leveraged private investment in to the area. |  | 24853500 | 21819000 | 20074488.61 | 92% | Transport improvements to: - A349 Gravel Hill & Dunyeats Roundabout - Darby's Corner - Poole Bridge - Townside Access - Hatch Pond (additional) - Broastone Way/ Cabot Lane (additional) - 5.15km of resurficed road - 5km of new cycle ways | On Target | - 3,000 new homes - 1,500 jobs - 80 HA unlocked development land - Generate up to £250m GVA | On Target
Boundary Roundabout | Bournemouth Borough Council | Bournemouth | Transport | 2020-06-08 | 2021-03-31 | -12.84% | Ongoing | Improvement to Boundary Roundabout which includes reducing the size of the roundabout, increasing the footways to install off road cycle and footways |  | 1931571.4 | 1618162.92 | 4200 | 0.2596% | Improvement to Boundary Roundabout which includes reducing the size of the roundabout, increasing the footways to install off road cycle and footways | Ongoing | - Help to enable the expansion of Bournemouth University and Arts University Bournemouth with a 27% increase in student numbers. - Reduce road casualties by 50%. - Improve journey time reliability. | On Target
Gillingham Growth | Dorset Council | Gillingham | Transport | 2018-04-01 | 2021-03-31 | 69.5% | Ongoing | Transport infrastructure improvements to support the housing and employment urban extension of Gillingham. |  | 3591227.33 | 3180227.33 | 415494.84 | 13.06% | Junction improvements on: - Shaftesbury Road/New Road - Newbury-High Street/Le Neuborg Way - SCOOT installation (Wyke Road, Station Road & King Road) - Sustainable transport improvements - The Enmore Green Link Road design - 1.079km of new cycle ways | On Target | - 1,800 new homes - 9 HA employment land unlocked - 2,500 jobs | On Target
Agri-tech Centre | Kingston Maurward College | Dorchester | Skills | 2015-11-01 | 2016-07-31 | 100% | Completed | Construction of a new cutting-edge Agri-Tech training facility. |  | 1200000 | 900000 | 900000 | 100% | Agri-Tech Centre including high spec workshop and machinery facilities - Fleet of tractors, including GPS tractor, plough, sprayer and variable rate drill | Delivered | - 40 apprentices trained per annum - 100 students trained per annum - 90 new jobs | On Target
Construction and Engineering Project | Bournemouth and Poole College | Bournemouth | Skills | 2019-10-14 | 2020-11-30 | 48.43% | Ongoing | Creation of a Regional Centre of Excellence for engineering and advanced manufacturing skills training, design and delivery. Creation of a Construction Hub for all construction trades at Bournemouth & Poole College’s North Road campus. |  | 653672 | 610000 | 59911 | 9.821% | Investment in machinery and resources in BPC's Engineering & Advanced Manufacturing area. Refurbishment of an existing workshop building to accommodate all construction wet trades at BPC’s North Road campus in Poole | On Target | -100 additional Apprenticeship starts - 98 additional full time students - Introduction of virtual welding to the curriculum for the 20/21 academic year - Introduction of new adult re-skilling / upskilling / CPD opportunities beginning in 21/22 and generating at least £40k per annum by 2024/25 -Reduce costs from September 2020 by at least £30k per annum | On Target
Outdoor Adventure Centre and Estate Refurbishment | Kingston Maurward College | Dorchester | Skills | 2019-10-14 | 2020-09-30 | 56.82% | Ongoing | • To build a climbing facility to support the needs of the college and the wider community. • To refurbish large commercial kitchen to ensure compliance, improving efficiency and health and safety. • To repair estate roads to facilitate safer access for pedestrians, public transport, cars and commercial vehicles visiting the college. |  | 200000 | 111675 | 111675 | 100% | Establishment of an Outdoor Education Centre Refurbishment of catering facility Repair of estate roads at the College | On Target | 300m2 Floor space created 3 new business start ups 2 permanent, paid full time equivalent jobs 1 volunteer positions 5 new trainees/ apprentices/ work placements + 1750 No. of visitors/tourists | On Target
Centre of Excellence for Motor Vehicle Technology | Weymouth College | Weymouth | Skills | 2019-07-01 | 2019-11-15 | 100% | Completed | Centre of Excellence for Motor Vehicle Technology is a transformational project aimed at future-proofing Weymouth College’s advanced Motor Vehicle workshop space and develop hybrid and fully electric vehicle facilities. |  | 250000 | 250000 | 251296.13 | 100.5% | -Develop and modernise 500msq of current workshop traning floor space -Replacing the current vehicle fleet with hybrid and fully electric vehicles -3 new technology vehicles (2 Hybrid and 1 fully electric) -12 second hand petrol and diesel vehicles -Two 2-post ramps with the existing ramps relocated to maximise available delivery space. -4-post MOT Ramp with a new MOT standard headlight beam setter installed alongside -Replacement tooling ,shelving and work-desks -Dedicated hybrid section -CPD MOT on-line training package training programme. | Delivered | - 30 jobs per annum - 30 retained jobs per annum - 20 up-skilled jobs per annum - 160 trainees/apprentices per annum - 10 new businesses | On Target
Engineering Centre of Excellence | Weymouth College | Weymouth College | Skills | 2019-10-14 | 2020-11-30 | 48.43% | Ongoing | To develop a new Engineering Centre of Excellence in Poundbury, Dorchester. The project will further enhance the College's engineering curriculum, allow for the development of the new engineering apprenticeship standards, and offer new new machinery to enhance pneumatic and mechatronic curriculum. |  | 605000 | 605000 | 375705.37 | 62.1% | Develop and modernise 500m2 of current stonemasonry workshop space in Poundbury, Dorchester . Update and modernise engineering equipment. Replace IT infrastructure and software for Engineering and Digital Media areas. | On Target | - 10 jobs, 10 business start ups, 30 permanent full time jobs, 30 retained jobs, 20 up-skilled jobs, 160 new apprentices/annum | On Target
Engineering & Manufacturing Project | Bournemouth & Poole College | Bournemouth & Poole | Skills | 2015-11-25 | 2016-10-31 | 100% | Completed | Upgrading Engineering & Manufacturing training facilities. |  | 895263 | 565150 | 564637 | 99.91% | - Upgrade training facilities to C rating (including cladding, replacement of windows, roof repairs). | Delivered | - 20 jobs per annum - 354 apprentices trained per annum - 227 students trained per annum | On Target
Finance & Business Services Project | Bournemouth & Poole College | Bournemouth & Poole | Skills | 2015-11-25 | 2016-10-31 | 100% | Completed | Upgrading of Financial & Business Services building and training facilities |  | 2567160 | 2000000 | 1998054 | 99.9% | - Upgrade training facilities to C rating - AutoCAD classrooms and 3D printing facilities - investment in lathe and milling areas | Delivered | - 40 jobs per annum - 50 apprentices trained per annum - 740 students trained per annum | On Target
Digital Design | Bournemouth and Poole College | Bournemouth | Skills | 2020-03-09 | 2020-06-30 | 46.9% | Ongoing | Address skills gap - students gain higher level production skills in animation, graphics, character design, game concepts and storyboarding. |  | 16800 | 16800 | 12527 | 74.57% | Purchase 28 graphic display tablets for media students | On Target | Upskill 256 students annually in areas such as animation, graphics, character design, game concepts and storyboarding. | On Target
Digital and Enterprise Innovation Hub | Bournemouth and Poole College | Bournemouth | Skills | 2020-01-28 | 2020-09-30 | 38.21% | Ongoing | Create two Hubs to provide a central focus at each site promoting the development of employability and enterprise skills. |  | 85928 | 85928 | 675 | 0.7855% | Create two Innovation Hubs located at each BPC site | On Target | Increased development of employability skills for 4000 students and apprentices | On Target
Innovation Studio | Arts University Bournemouth | Poole | Innovation and Skills | 2017-04-01 | 2020-09-30 | 88.11% | Ongoing | Creation of a new state of the art incubation facility studio to support digital and creative industries in Dorset. |  | 2800000 | 1400000 | 603921.54 | 43.14% | Construction and fit out of Innovation Studio on AUB land 502.75sqm learning floor space created | On Target | - 40 graduate start ups - 34 business start ups - 40 jobs - 20 new learners assisted per annum - 635sqm floor space created - 0.16 HA land unlocked | On Target
LapSafe Learning Level 3 | Arts University Bournemouth | Bournemouth | Skills | 2019-10-14 | 2020-02-29 | 100% | Completed | Funding to increase digital literacy and creative skills outside and beyond the classroom amongst L3 AUB students through providing access to a bespoke set of specialist Mac laptops. |  | 66241 | 51000 | 51000 | 100% | Procurement and installation LapSafe installation by March 2020 Procurement of 20 Apple Laptops with Full Office and Adobe Software | On Target | c300 L3 students p/a will benefit and have access to the new system. Delivery of a high quality and nationally regarded Foundation in art and design one year programme. Development of a cohort of FE learners who have advanced digital skills. Increased digital literacy of AUB students. Maintain OfSTED ratings with regards to skills and progression | On Target
Orthopaedic Research Institute (ORI) | Bournemouth University | Bournemouth | Innovation and Skills | 2015-10-01 | 2020-09-30 | 91.68% | Ongoing | Phase 1: Purchase of equipment to establish the Orthopaedic Research Institute. Phase 2: Purchase of additional equipment and expansion of ORI as a global gateway. |  | 1650000 | 1650000 | 1415240.65 | 85.77% | Phase 1: Purchase of key pieces of world leading equipment (Laser Speckle Contrast Imager, OSSIM Sim-K total knee replacement virtual reality simulator, Virtamed virtual reality arthroscopy simulator, Matek GRAIL (Gait real-time analysis interactive lab, Primus RS - BTE Systems) - 247.6 m2 training/learning floor space created Phase 2: Purchase of additional equipment (Ultrasound scanner, IT software solution, 5 Wattbikes, Activity monitors & shockwave equipment, Open surgery simulators for hip and knee surgery, Specialist robotic hip surgery simulator, Specialist robotic training portal simulator, 2 portable 3D imaging body scanners) - Expansion of facilities | On Target | - £1.8m private leverage investment - £1.3m public leverage investment - £76k third sector leveraged investment - 86 jobs - Train 50 surgeons & health professionals per annum - 100 clinical trials participants per annum - 68 enterprises receiving non-financial support - 2 business created | On Target
Institute for Medical Imaging and Visualisation | Bournemouth University | Bournemouth | Innovation and Skills | 2018-01-01 | 2020-03-31 | 100% | Completed | Institute for Medical Imaging and Visualisation will be a hub for Medical Imaging technology programme and research development, in partnership with education, clinical practice and commercial partners. |  | 1400000 | 1400000 | 1401275 | 100.1% | -MRI Scanner - Direct metal laser sintering machine - VR equipment - 3D/4D ultrasound equipment - Medical grade 3D printers -5000 sqm of floor space created -0.8 HA unlocked land | Delivered | -10.4 jobs -1154 new learners/apprentices - 8 new business start-ups - £5.25 private leverage investment - £10.5 public leverage investment - £2m GVA from salaries to local economy | On Target
Eden Portland | MEMO, Albion Stone & Eden Project | Portland | Tourism | 2017-04-01 | 2019-03-31 | 100% | Completed | Development of an art gallery, a new scientific institution, and an interactive visitor destination within a working mine. |  | 1600000 | 1000000 | 1000000 | 100% | Design, development and planning work to enable project. | Delivered | - £15.8m leveraged funds - 325k visitors per annum - 30 apprentices | On Target
Jurassica | Jurassica | Portland | Tourism | 2015-04-01 | 2015-04-30 | 100% | Completed | Funding to support design and planning work for proposed major new tourist attraction in Portland. |  | 300000 | 300000 | 300000 | 100% | Feasibility study and bidding document for HIF application. | Delivered |  | Delivered
Mary Anning Wing | Lyme Regis Museum | Lyme Regis | Tourism | 2017-07-01 | 2018-03-31 | 100% | Completed | Funding towards the building of the Mary Anning Wing of Lyme Regis to enhance learning, exhibition and café space. |  | 1464250 | 56250 | 56250 | 100% | Mary Anning Wing extension to Lyme Regis Museum includes: - learning space - extended exhibition - expanded retail space - public toilets and a lift | Delivered | - 2.5 jobs - 28,500 visitors per annum | On Target
Shire Hall | West Dorset District Council | Dorchester | Tourism | 2017-06-01 | 2018-04-30 | 100% | Completed | Restoration of a Grade 1 listed building as a visitor attraction. |  | 3006264 | 56250 | 56250 | 100% | Improvements to the Shire Hall building to include: - 2 apartments for rent - exhibition & law courts refurbished - café & shop | Delivered | - 5 new jobs - 1 apprentice per annum - 50 volunteer positions - 32k visitors per annum - 2 business starts | On Target
Swanage Pier | Swanage Pier Trust | Swanage | Tourism | 2017-08-01 | 2020-03-31 | 100% | Completed | Restoration of Swanage Pier to secure education and retail facilities. |  | 2213069 | 56250 | 56250 | 100% | - Repairs and restoration of Swanage Pier - Refurbishment of an existing Grade 2 listed building | On Target | - Increase of 12,500 visitors annually - 26 jobs - 365 volunteer positions | On Target
Digital Dorset Pilot | Bournemouth, Christchurch and Poole Council | Bournemouth | Digital/ Internet Infrastructure | 2019-09-01 | 2021-03-31 | 42.11% | Ongoing | 5G and digital infrastructure in the Lansdowne area of Bournemouth. |  | 1333000 | 1000000 | 44606 | 34% | - Core Network, Hardware and Software - 5G equipment - Ducting and fibre | On Target | - 400 new jobs, with 700 created within 12 years | On Target
Lansdowne Business District | Bournemouth, Christchurch and Poole Council | Bournemouth | Digital/ Internet Infrastructure | 2017-04-01 | 2021-03-31 | 77.12% | Ongoing | Develop Lansdowne into a major commercial business district through transport upgrade, public realm, digital infrastructure. |  | 11250000 | 7000000 | 1688930 | 24.13% | Infrastructure and urban realm improvements: - Improving street scene - Restricting motor vehicle movements - Creation of public space along Holdenhurst Road - Improved walking and cycling links to the main rail station | Behind Programme | - 2450 jobs - 95 Trainees/Apprentices - 1.72 HA land unlocked - 93 new businesses - 1110 business start ups | Behind Programme
Smart Place Investment Plan | Bournemouth, Christchurch and Poole Council | Bournemouth | Digital/ Internet Infrastructure | 2020-04-01 | 2021-03-31 | 8.242% | Pre-contract | Produce a Smart Place Investment Plan that will be used to attract significant inward investment of up to £1bn for Dorset to create a Smart Place, implementing associated digital connectivity and technologies. |  | 460000 | 380000 | 4000 | 1.053% | A Smart Place Investment Plan gaining inward investment for Dorset, covering: - Assessment of business models and revenue-raising opportunities - Providing evidence to support bids for major government investment - Costings for implementation and management - Assessment of economic, social and health benefits. - Assessment of potential service cost savings (LA's / NHS) | Pre-contract | - Smart Place investment Plan to generate up to £1bn inward investment | Pre-contract
Innovation Hub | Dorset Council | Dorset Innovation Park | Employment | TBD | TBD | 0% | Pre-contract | Creation of a innovation hub which would enable Defence to have a single open plan office and the ability to co-locate with companies or reps from companies – to initiate and develop projects |  | 5000000 | 1500000 | 0 | 0% | - Modular building at the Dorset Innovation Park | Pre-contract | To be confirmed once Full Business Case has been submitted | Pre-contract
Literary & Scientific Institute (LSI) | Bridport Area Development Trust | Bridport | Employment | 2017-04-01 | 2018-03-31 | 100% | Completed | Restoration and conversion of the LSI building to support provision of services for local economic growth. |  | 2702900 | 56250 | 56250 | 100% | Upgrade of LSI building to include: - incubation workspaces - work hub space - flexible meeting and networking space - full fibre broadband | Delivered | - 9 direct jobs - 2 apprentices - Annual reinvested income of £225k | On Target
Quadrant - Dorset Innovation Park | Purbeck District Council | Winfrith | Enterprise | 2016-10-01 | 2018-03-31 | 100% | Completed | Purchase of land and build of workshop units to support businesses at Dorset Innovation Park, Enterprise Zone. |  | 2800161 | 600000 | 600000 | 100% | - 6 HA land unlocked - 20 workspace units available for occupation | Delivered | - 60 jobs - 20 businesses relocated/ created | On Target
Holes Bay | Borough of Poole Council | Poole | Enabling Works | TBC | 2020-10-31 | 0% | Pre-contract | Enabling works to unlock major housing site and employment land. |  | 16300000 | 5000000 | 8450 | 0.169% | - Acquisition of the Holes Bay site by the public sector - 16 HA of currently unused land unlocked, regenerated and developed for economic use | Pre-contract | - 830 homes - at least 10% of these to be affordable homes - 761 sqm of retail space over 15 years - 40 new jobs accommodated on the site - £5 million of land value uplift - £1 million of new residents’ additional annual spend per year in the local area - £56 million of temporary GVA impact during the construction period (up to Q4 2024), and more than £2.3 million of annual GVA impact thereafter | Pre-contract
Western Growth Corridor | Weymouth & Portland Borough Council | Weymouth | Enabling Works | 2015-11-26 | 2017-03-31 | 100% | Completed | Preparatory work into planned development of public assets. |  | 600000 | 600000 | 593957 | 98.99% | Preparatory work to inform and create the Western Growth Corridor Strategy. | Delivered | - £11m leverage of public assets to deliver WGC Strategy - 56 HA land unlocked - 2,700 jobs - 400 homes | On Target
Stewarts Agri-Tech Glasshouse | D Stewart & Son LTD | Christchurch | Innovation | 2019-06-01 | 2019-03-31 | 100% | Completed | Agritech facility with automated features to enable increased turnover, job creation and more sustainable horticultural production. |  | 1580556 | 297000 | 298350 | 100.5% | - 9,000 sqm growing facility - Agri-Tech features with improved automated materials handling and computer-controlled varied heating and shading zones. | On Target | - Increased productivity and more sustainable horticultural production. - Range of plants capable of being produced increased by a factor of 4x. - 5 jobs - 20 work placements - 11 volunteers - 0.9 HA unlocked land | On Target
IT Infrastructure Upgrade (KMC) | Kingston Maurward College | Dorchester | Skills | TBC | 2021-03-31 | 0% | Pre-contract | IT upgrade at the KMC college. IT infrastructure across the campus fully upgraded, providing suitable support for students and development of the estate, and prepared for 5G and Superfast capacity as part of Superfast Dorset rollout. |  | 199733 | 124733 | 825 | 0.6614% | - 2 New Servers - Additional Memory - Desktop Refresh (60 PCs) - Switches upgrade from 100MB to 1GB (20 Switches) - WIFI Access Points upgrade from 100MB to 1GB (68 WAPs) - Replacement Server Room UPS (6 UPS) - Campus UPS Refresh (10 per year) - WIFI in Fields & WIFI by the Lake - Maurward Hall Refurb - New Backup Server - New Barn Network Upgrade | Pre-contract | - 4 new jobs, 4 retained jobs and 70 up-skilled jobs - 5% productivity value increase by FY20/21 - 1 business start-up and 1 business relocated to LEP region - 2 new trainees/apprenticeships/work placements - 5000 visitors/tourists - Attracting additional students: up to 82 over a 5-year period - Increased speed of network - Improved customer and student experience | Pre-contract
New Green Classroom (KMC) | Kingston Maurward College | Hengistbury Head | Skills | TBC | 2021-03-31 | 0% | Pre-contract | Establish a joint Learning Centre between KMC and Hengistbury Head (BCP Council) |  | 69711 | 69711 | 825 | 1.183% | Establishment of new Green Room facilities with 20 sqm floor space for the purpose of offering nature and environmental related activities and education - new accessible structure, including two clad shipping containers, connecting covered deck area, including IT equipment. | Pre-contract | - 1 new business start-ups - 2 new jobs - 2 retained jobs - 2 volunteer positions - 2 new trainees/apprenticeships/work placements - 3000 visitors/tourists per annum - Delivery of minimum of 15 commercial sessions expected per annum - Outdoor learning sessions delivered to 150-300 young people per annum - Delivery of KMC based group sessions – minimum of one per annum | Pre-contract
Histopathology Diagnostic Hub for Dorset | Royal Bournemouth Hospital | Royal Bournemouth Hospital | Health & Wellbeing | TBC | 2021-03-31 | 0% | Pre-contract | Embedding a Histopathology Diagnostic Hub within the wider development of a Pathology Hub in Dorset. |  | 22381300 | 2281300 | 1350 | 0.05918% | - Histopathology Diagnostic Hub for Dorset fully operational - 500 m2 of floorspace of high quality histopathology laboratory, and associated support space | Pre-contract | - 120 safeguarded jobs on the Wessex Fields site, with high ratio of upskilled jobs - Delivering wider societal benefits from quicker access to diagnosis, and more personalised treatment, based upon having modern, cutting edge Pathology | Pre-contract
Centre of Excellence for Construction Skills | Weymouth College | Weymouth | Skills | 2020-04-03 | 2021-01-29 | 9.302% | Pre-contract | Enhance College facilities to allow it to continue to deliver Construction apprenticeships that meet the new Apprenticeship standards. |  | 750000 | 750000 | 1350 | 0.0018 | • Extra capacity in fully remodelled and upgraded accommodation | Pre-contract | • Double the number of Construction apprenticeships from 80 a year to 160. • Double the number of Construction full- and part-time students (130 to 260) as well as enable upgrading of skills for existing Construction workers • Create a Construction HNC/HND for up to 20 students a year. | Pre-Contract

## Growing Places Fund
DORSET LOCAL ENTERPRISE PARTNERSHIP
Growing Places Fund Project Dashboard
REPORT DATE
2020-05-01
PROJECT INFORMATION | [9 empty] | FINANCIAL INFORMATION |  |  |  |  | OUPUTS AND OUTCOMES
PROJECT NAME | PROJECT DELIVERY PARTNER | PROJECT LOCATION | PROJECT THEME | PROJECT START DATE | PROJECT END DATE | % TIME COMPLETE | PROJECT STATUS | PROJECT SUMMARY |  | TOTAL PROJECT BUDGET |  | TOTAL GPF FUNDING | REPAYMENT TO DATE | % REPAYMENT TO DATE | FORECAST OUTPUTS | PROGRESS TOWARDS FORECAST | FORECAST OUTCOMES | PROGRESS TOWARDS FORECAST
Alder Hills | Bournemouth Churches Housing Association | Poole | Business Support | 2014-02-28 | 2019-02-28 | 100% | Completed | This scheme is for the purchase and refurbishment of the former “Remploy” factory at Alder Hills, Poole, to develop a Business Development Hub and Social Enterprise Centre of Excellence along with the catering and café and conferencing services. |  | 775000 |  | 775000 | 775000 | 100% | 1,300 sqm of refurbished co-working space and provision of co-working space together with catering and conferencing facilities, including a café. | Delivered | 26 full-time jobs created, provision of business support, office rental, co-working space, cataring and training facilities | Delivered
Bionanovate | Bionanovate, Ltd | Poole | Refurbishment | 2015-12-23 | 2020-12-23 | 87.08% | Ongoing | The loan is for the purchase, refurbishment and development of the former Sunseeker building at Mannings Heath Road, Poole. Bionanovate is then to locate its three businesses on the site, renting out any additional space to other businesses. |  | 1700000 |  | 1700000 | 0 | 0% | The loan is for the purchase, refurbishment and development of the former Sunseeker building at Mannings Heath Road. Creation of 2,384 sqm floor space. | On Target | 50 full-time jobs created. | On Target
Boscombe Regeneration, Community Land Trust | Bournemouth Borough Council | Boscombe, Bournemouth | Housing | 2013-05-07 | 2015-10-16 | 100% | Completed | The development of 11 affordable, low energy family homes at Gladstone Mews in Boscombe, including the added value of the inclusion of latest fire suppression systems, allotments and community orchard. |  | 1194394.31 |  | 1194394.31 | 1194394.31 | 100% | 11 affordable, low energy homes | Delivered | 20 full-time jobs created | Delivered
Castle Court, Ospray Quay | Weymouth & Portland Borough Council | Portland | Public Realm | 2013-04-04 | 2014-07-31 | 100% | Completed | The development of the Castle Court Public Realm works at Osprey Quay, Portland. The project focused on soft and hard landscaping to create the new Liberty Square in front of the derelict Navy Canteen Building, |  | 500000 |  | 500000 | 500000 | 100% | Provision of a major aesthetic enhancement to the area Osprey Quay area. | Delivered | - 21 apartment units within the existing Canteen building for shared ownership - 47 residential houses and flats for private sale | Delivered
Cobham Gate | Glenbeigh Developments Ltd | Wimborne | Enabling Works | 2016-04-21 | 2021-04-21 | 80.56% | Ongoing | To enable access to the commercially strategic site and to provide supporting infrastructure, particularly the maintenance of roads within the site, off-site road improvements, operational services, drainage and landscaping and to deliver serviced plots at the Cobham Gate. |  | 1500000 |  | 1500000 | 500000 | 33.33% | 8.4ha site development and plot preparation for sale | On Target | Approximately 40,000 sqm of floor space. | On Target
Field International | Field International | Poole | Other | 2013-05-13 | 2018-05-13 | 100% | Completed | This scheme is to facilitate refinancing to enable the development of a new building. |  | 2315000 |  | 2315000 | 2315000 | 100% | Refinancing completed | Delivered | 50 jobs safeguarded and 10 jobs created. including some apprenticeship positions. Expansion of the business and increased turnover. | Delivered
Hamworthy | Borough of Poole | Hamworthy, Poole | Public Realm | 2015-12-22 | 2021-02-28 | 100% | Ongoing | Construction of a pedestrian / cycle footbridge over a branch railway line allowing access from Lower Hamworthy to Hamworthy Park, together with a new road crossing and pedestrian improvements to Blandford Road in Hamworthy. |  | 660000 |  | 660000 | 660000 | 100% | Construction of a pedestrian / cycle footbridge | Delivered | Un-lock the next phase of development in the Hamworthy regeneration area, Link the new developments in the Hamworthy regeneration area to the existing facilities/green space in Hamworthy Park, Facilitate and encourage active/sustainable travel | Delivered
North Dorset Business Park | Dorset County Council | Sturminster Newton | Enabling Works | 2013-03-01 | 2018-03-01 | 100% | Completed | Site servicing works to create serviced plots for owner occupiers to build workspace and a high quality business park targeted at food production. |  | 800000 |  | 800000 | 800000 | 100% | 7,400 m² of new employment floor space | On Target | 250 full-time jobs created | On Target
Ultrafast Broadband | Dorset County Council | Dorset | Digital/ Internet Infrastructure | 2017-04-01 | 2020-03-31 | 100% | Ongoing | To deliver superfast broadband to Dorset Enterprise Zone, Bournemouth Airport and the Western Growth area. |  | 6585000 | 6585000% | 2000000 | 52333 | 2.617% | Pure fibre gigabit (1,000Mbps) connectivity across the Enterprise Zone, and Aviation Park, Bournemouth Airport, 91% coverage to the priority premises, Total superfast coverage across Bmth, Dorset and Poole to increase to 98%, 3,856 premises to have access to at least superfast (30Mbps+) speed, 3,589 of those with access to gigabit speeds | On Target | Contribute to realisation of strategic prosperity and economic growth benefits across Dorset, directly support the creation of new jobs at Dorset Enterprise Zone and Bournemouth Airport | On Target
Annimal Park | Kingston Maurward College | West Dorset | Tourism | 2019-01-01 | 2023-12-31 | 26.63% | Ongoing | Construction of the Animal Park completed, launch on 18 October 2019. Loan fully drawdown. |  | 250000 |  | 250000 | 15625 | 6.25% | 3 x part-time roles created. 2 x full-time jobs and 1 x part-time job safeguarded. | On Target | Increased length of operating season. Improved revenue and footfall, both in terms of length of operating season and also in terms of wet weather accessibility and activity. | On Target

## Dorset Gateway
DORSET LOCAL ENTERPRISE PARTNERSHIP
Dorset Gateway Project Dashboard
REPORT DATE
2020-02-10
PROJECT INFORMATION | [9 empty] | FINANCIAL INFORMATION |  |  | OUPUTS AND OUTCOMES
PROJECT NAME | PROJECT DELIVERY PARTNER | PROJECT LOCATION | PROJECT THEME | PROJECT START DATE | PROJECT END DATE | % TIME COMPLETE | PROJECT STATUS | PROJECT SUMMARY |  | TOTAL PROJECT BUDGET | SPENT TO DATE | % SPENT TO DATE | FORECAST OUTPUTS | PROGRESS TOWARDS FORECAST | FORECAST OUTCOMES | PROGRESS TOWARDS FORECAST
Custom Brokerage Service | Dorset Chamber of Commerce and Industry | n/a | Business Support | 2018-06-01 | 2021-03-31 | 59.86% | Ongoing | To be the key access point for brokerage to a wide-range of business support services in the Dorset county area |  | 218910 | 120357 | 54.98% | 2,300 businesses recorded and engaged 450 businesses brokered into external business growth services 200 businesses taking up external business growth services | On Target | 100 businesses reporting growth as a result of the support provided 80% satisfaction level with businesses engaged with | On Target
Bid Writing Support Service | BrooksKebbey Ltd. | n/a | Business Support | 2018-04-01 | 2021-03-31 | 62.1% | Ongoing | Supporting Dorset businesses to write and submit bids for funding that will enable growth through innovation and contribute to our goal of improving productivity in Dorset. |  | 120000 | 80000 | 66.67% | Minimum of 80 days support provided Minimum of 250 businesses engaged in bid writing support activities per annum Minimum of 10 grant funding applications, involving Dorset-based businesses, submitted to UK funders 80% satisfaction rate from users of the service | On Target | Number of businesses using the service successful with their application | On Target
Customer Relationship Management System | Alcium Software | DLEP | Business Support | 2020-04-01 | 2021-03-31 | -14.01% | Ongoing | The CRM system will enable DLEP to build and manage a comprehensive log of all business support engagements that access the Dorset Gateway services. |  | 15000 | 12500 | 83.33% | All DLEP engagement activity captured on CRM Project management data across all delivery programmes captured | On Target | Firm-level data for medium and high-level intensity engagements recorded Improved reporting across all delivery programmes | On Target
Scale-up Support | Finn Morgan | DLEP | Business Support | 2020-04-01 | 2021-03-31 | -14.01% | Pre-contract | Identify Dorset-based scale-up businesses and develop a programme/workpackage of targeted support Maintain a strong overview of relevant Government policy in relation to business support, including activity focused on scale-up businesses. |  | 25000 | 0 | 0% | All Dorset-based scale-up businesses identifiied and contacted Pilot programme established 30 scale-up businesses engaged in pilot programme | Pre-contract | Businesses taking part in scale-up programme reporting increased confidence in growth potential | Pre-contract
Business Engagement | Finn Morgan | DLEP | Business Support | 2018-08-13 | 2021-03-31 | 56.82% | Ongoing | Contribute to and support the wider development and delivery of the LEPs business engagement strategy |  | 0 | 0 | 0% | Development of business engagement strategy Development of the LEPs pipeline of SME projects for targeting funding opportunities made available by Government to deliver the Industrial Strategy. | On Target | Increased business engagement in Dorset LEP programmes Pipeline of SME projects in place | On Target

## Dorset Innovation Park
DORSET LOCAL ENTERPRISE PARTNERSHIP
Dorset Innovation Park Project Dashboard
REPORT DATE
2020-05-01
PROJECT INFORMATION | [9 empty] | FINANCIAL INFORMATION |  |  | OUPUTS AND OUTCOMES
PROJECT NAME | PROJECT DELIVERY PARTNER | PROJECT LOCATION | PROJECT THEME | PROJECT START DATE | PROJECT END DATE | % TIME COMPLETE | PROJECT STATUS | PROJECT SUMMARY |  | TOTAL PROJECT BUDGET | SPENT TO DATE | % SPENT TO DATE | FORECAST OUTPUTS | PROGRESS TOWARDS FORECAST | FORECAST OUTCOMES | PROGRESS TOWARDS FORECAST
Local Development Order | Stride Treglown (Lead: Purbeck District Council) | Dorset Innovation Park | Enabling Works | 2017-12-05 | 2018-11-28 | 100% | Completed | Professional fees associated with delivery of LDO covering detailed site investigations and surveys, ecology, landscape and design strategies, environmental impact assessments and planning fees. |  | 350000 | 284501 | 81.29% | Dorset Innovation Park masterplan Design Guide Statements of Reason Detailed site investigation surveys Ecology, landscape, travel and design strategies Approval of LDO by Purbeck Planning Committee 28/11/18 | Delivered | Approval of a Local Development Order that will streamline planning permission on the Park to 28 days or less. A USP that no other strategic economic development area in Dorset has. | Delivered
Travel Plan | Contractor tbc (Lead: tbc) | Dorset Innovation Park | Transport | 2019-09-01 | 2024-03-31 | 0% | Pre-contract | Delivery of modal shift through the development of a detailed Travel Plan for Dorset Innovation Park, appointment of a Travel Plan Coordinator and company Travel Plan champions. Project delayed due to changes/lack of resourcing at Dorset Council. |  | tbc | 0 | 0% | New footways and cycleways to encourage modal shift Travel Plan Strategy for Dorset Innovation Park Travel Plan Coordinator | Pre-contract | Achievement of Travel Survey targets in 5 years (10% reduction in car travel) | Pre-contract
Enterprise Zone Strategic Committee | Dorset Council | Dorset Innovation Park | Governance | Ongoing | Ongoing | n/a | Ongoing | The DLEP EZ Board maintains a focus as an ‘investment board’ with oversight of the DLEP Enterprise Zone Programme. |  | TBD | TBD | TBD | The DLEP EZ Board is concerned with overall management of the EZ Programme. It has 3 main decision-making functions: • Granting business rate relief on an individual company basis. • Supporting wider investment packages for the site – to unlock growth and realise best return. • Management of the EZ business rate growth investment fund over the medium to long term. | Ongoing | Its primary aim is to unlock additional investment for Dorset through growth of the EZ site (and concurrent business rates growth return). | Ongoing
Enterprise Zone Strategic Investment Plan | Contracted to Cushman and Wakefield | Dorset LEP | ROI | 17 04.2020 | 17.05.2020 | 30% | Ongoing | To identify the projected returns from the Business Rate uplift and thus the potential for borrowing for reinvestment in the business park. |  | 15000 | 0 | 0 | Identify the uplift from existing developments. Compare this to original plan submitted to BEIS. Identify potential for future growth. Model potential for borrowings to speed up investment and growth. | Ongoing | Increase in office and production space on the Innovation Park. Increase in jobs (as yet undetermind). Increase in value of the real estate. | Ongoing

## ESIF (hidden)
DORSET LOCAL ENTERPRISE PARTNERSHIP
European Structural Infrastructure Fund Project Dashboard
REPORT DATE
2020-05-01
PROJECT INFORMATION | [11 empty] | FINANCIAL INFORMATION |  | OUPUTS AND OUTCOMES
| Priority Axis | PROJECT NAME | PROJECT DELIVERY PARTNER | PROJECT LOCATION | PROJECT THEME | PROJECT START DATE | PROJECT END DATE | % TIME COMPLETE | PROJECT STATUS | PROJECT SUMMARY |  | TOTAL PROJECT BUDGET | TOTAL ESIF FUNDING | FORECAST OUTPUTS | PROGRESS TOWARDS FORECAST | FORECAST OUTCOMES | PROGRESS TOWARDS FORECAST
ERDF | 1 | AUB Innovation Studio | Arts University Bournemouth | Bournemouth | Innovation | 2017-01-01 | 2019-12-31 | 100% |  |  |  | 1199930 | 599965
ERDF | 3 | Dorset Business Growth (Dorset Growth Hub) | WSx Enterprise | Dorset County | Business Support | 2016-01-01 | 2020-06-30 | 96.35% |  | Comprehensive business support package targets key sectors |  | 12641345 | 6320673
ERDF | 9 | Technical Assistance | Dorset Council | Dorset County |  |  |  | 100% |  | Formation of a small technical assistance team to ensure publicity and promotion of ESIF opportunies is undertaken across Dorset LEP area and to advise and support under-represented sectors to apply to the programme |  | 94842 | 47421
ERDF | 4 | Low Carbon Dorset | Dorset Council | Dorset County |  | 2016-09-01 | 2020-10-31 | 87.97% | Ongoing | The Programme provides free technical advice and financial support to local Business, Community and Public Sector organisations to deliver carbon reduction projects in Dorset |  | 6437722 | 3218864 | • Free Workshops and Technical support to help organisations identifying, develop and deliver successful low carbon projects, products or processes. • A £2.15 Million Low Carbon Dorset Fund, to provide grants towards project implementation | On Target | • Support over 100 businesses to reduce energy and utilise renewable energy technologies, • Increase Dorset’s renewable energy capacity by at least 3 Mega Watts • Reduce energy consumption in public sector buildings by over 2 Giga Watts hours/year • Reduce Dorset’s carbon footprint by over 2,650 tonnes Carbon Dioxide /year • Encourage development of at least 5 new low carbon products or applications | On Target
ESF |  | Skills for Young People | CSW Group | Dorset County | Skills | 2019-04-01 | 2021-07-31 | 46.48% | Ongoing | Supporting over young people (15-24 years) not in employment, education or training (NEETS) to develop new skills and move towards apprenticeships or other training |  |  | 900000 | 572 learner assessments & plans 57 progression paid employment 194 progression education 29 progression apprenticeship 29 progression traineeship | On Target |  | On Target
ESF |  | Skills Support to the Unemployed | Twin | Dorset County | Skills | 2019-04-01 | 2021-07-31 | 46.48% | Ongoing | Supporting unemployed or economically inactive people (mainly 25 years upwards) to return to the labour market |  |  | 450000 | 297 learner assessments & plans 89 progression paid employment 24 progression education 30 progression apprenticeship 6 progression traineeship | On Target |  | On Target
ESF |  | Skills Support for the Workforce | Serco | Dorset County | Skills | 2019-04-01 | 2021-07-31 | 46.48% | Ongoing | Providing skills support for the workforce in small businesses |  |  | 450000 | 236 learner assessments & plans 12 progression paid employment 24 progression education 12 progression apprenticeship 47 progression within work 1 LEP agreed development plan (research project) | On Target |  | On Target
ESF |  | Dorset Community Training Grants | Groundwork | Dorset County | Skills | 2019-04-01 | 2021-07-31 | 46.48% | Ongoing | Awarding over £1m in community grants of £5,000 to £20,000 for charities and small organisations to help those furthest from the labour market with advice, guidance or training. |  |  | 1260000 | 893 learner assessments & plans 152 progression paid employment 125 progression education | On Target |  | On Target

## Careers and Enterprise Comp
DORSET LOCAL ENTERPRISE PARTNERSHIP
Careers and Enterprise Company Project Dashboard
REPORT DATE
2019-12-05
PROJECT INFORMATION | [9 empty] | FINANCIAL INFORMATION |  |  |  | OUPUTS AND OUTCOMES
PROJECT NAME | PROJECT DELIVERY PARTNER | PROJECT LOCATION | PROJECT THEME | PROJECT START DATE | PROJECT END DATE | % TIME COMPLETE | PROJECT STATUS | PROJECT SUMMARY |  | TOTAL PROJECT BUDGET | TOTAL CEC FUNDING | SPENT TO DATE | % SPENT TO DATE | FORECAST OUTPUTS | PROGRESS TOWARDS FORECAST | FORECAST OUTCOMES | PROGRESS TOWARDS FORECAST
Enterprise Adviser Network | Bournemouth, Christchurch and Poole Council (BCP) and Dorset Council | Dorset County | Skills | 2016-04-01 | 2020-08-31 | 100% | Ongoing | Dorset LEP is working with The Careers and Enterprise Company (CEC) and local authority partners to develop a Dorset wide Enterprise Adviser Network (EAN). Its purpose is to create powerful, lasting connections between local businesses, schools and colleges, including Special Educational Needs and Disability (SEND) provision, in the area. The network is intended to inspire and motivate young people, including those with SEND, supporting them to make informed choices about their future. |  | £170,000 (including in kind) | 97500 | 167000 | 100% | 3.5 Enterprise Coordinators | On Target | - Recruit additional Enterprise Advisers across Dorset - All EAN schools and colleges to be matched to an Enterprise Adviser | On Target
Careers Hub | Bournemouth, Christchurch and Poole Council (BCP) and Dorset Council | Dorset County | Skills | 2019-09-01 | 2020-08-31 | 100% | Ongoing | Dorset LEP is working with The Careers and Enterprise Company (CEC) to utilise additional funding and resource to enhance and support school performance against the Gatsby Benchmarks. The Hub works with 40 schools within the established Enterprise Adviser Network, supporting schools to engage with the careers agenda and learn from best practice. |  | 120000 | 60000 | 150000 | 100% | 1 Careers Hub Lead (Dorset LEP) 1 Enterprise Coordinator (Dorset LEP) + Enterprise Coordinators based in Dorset Council and BCP Council | On Target | At least an average of 4 benchmarks fully achieved across all Hub schools and colleges by the end of the 2019-20 academic year | On Target

## Data
Project Status
Pre-contract
Ongoing
Completed
Project Theme
Business Support
Cultural Sector
Digital/ Internet Infrastructure
Employment
Enabling Works
Enterprise
Flood Management
Health & Wellbeing
Housing
Innovation
Public Realm
Refurbishment
Skills
Tourism
Transport
Other
Outputs/Outcomes
Pre-contract
Behind Programme
On Target
Delivered